## Dashboard
FBS Pay - OPS Web App Development Dashboard
Project Owner: Thea Consignado ¦ Sep 15, 2026 to Nov 30, 2026 ¦ 11 weeks, 23 tasks
OVERALL PROGRESS |  | PLANNED BY END OF THIS WEEK |  | AGAINST PLAN (POINTS) |  | TASKS DONE
39.14% |  | 38.74% |  | 0.39267 |  | 1 / 23
Weighted by effort days |  | Week 4 of 11 |  | On plan |  | 7 weeks left
Progress by work stream |  |  |  |  | Task status
Work stream | Effort (days) | Actual % | Planned % |  | Status | Tasks
Foundation | 37 | 59.05% | 100% |  | Done | 1
Workforce and time | 50 | 45% | 74% |  | In progress | 20
Payroll and compliance | 56 | 40% | 0% |  | In testing | 0
Portals, platform and launch | 48 | 16.67% | 0% |  | Not started | 2
All streams | 191 | 39.14% | 38.74% |  | Behind plan | 8
[5 empty] | Total tasks | 23
Charts update when you change Status on the Tracker sheet and enter Actual % on the Weekly sheet.

## Tracker
FBS Pay - OPS Web App Development Tracker
Project Owner: Thea Consignado ¦ Tasks, schedule, and progress for the 11-week build, target finish Nov 30, 2026
Project owner |  | Thea Consignado |  | HOW TO USE
Project start date |  | 2026-09-15 |  | 1. Set the project owner and start date (C3, C4). Week 1 starts 15 Sep 2026; week 11 ends 30 Nov 2026 (target finish).
Report date (default = today) |  | 2026-10-07 |  | 2. Pick a Frontend status (column O) and a Backend status (column P) for each task. Leave blank if not applicable. Status (I) and Progress % are calculated as the average of the two (see Lists sheet).
Current week (0 = not started) |  | 4 |  | 3. At the end of each week, copy Overall progress (Tracker J32) into the Weekly sheet, column D.
Blue text on yellow = editable. Weeks and effort days are planning estimates; change them freely (columns D to F).
ID | Work stream | Task | Start wk | End wk | Effort (days) | Start date | End date | Status | Progress % | Planned % (this week) | Against plan (pts) | Flag | Notes | Frontend status | Backend status
T01 | Foundation | Project setup, architecture, UI/UX foundation | 1 | 1 | 5 | 2026-09-15 | 2026-09-21 | Done | 100% | 100% | 0 |  | Laravel 12 + Inertia/React + Fortify + Spatie. Ops layout (AppShell, sidebar, topbar), shared UI kit, and company brand/theme (BrandLogo, brandTheme) in place. | Done | Done
T02 | Foundation | Database design and multi-tenant setup | 1 | 3 | 8 | 2026-09-15 | 2026-10-05 | In progress | 50% | 100% | -50 | Behind plan | Migrations done: companies, branches, employees, activity_logs, users tenancy, permission tables, BelongsToCompany. Tables for attendance, leave, payroll, loans etc. not yet created (no new migrations since last update). |  | In progress
T03 | Foundation | Login, password reset, roles and permissions | 1 | 3 | 8 | 2026-09-15 | 2026-10-05 | In progress | 65% | 100% | -35 | Behind plan | Backend live: Fortify login/forgot/reset with role-based landing (dashboard or ESS), active-user middleware, 6 roles via Spatie. Capabilities reworked: Payroll Admin payroll-only (reads time/output/leave via Payroll Inputs), Manager team-scoped, new permissions (profile.view, employees.pay.view, attendance.import, reports.workforce.view). Auth, security and profile feature tests exist. Role editing UI still on mock data. | In testing | In progress
T04 | Foundation | User accounts, access and activity logs | 2 | 3 | 5 | 2026-09-22 | 2026-10-05 | In progress | 65% | 100% | -35 | Behind plan | User Access page (FE, mock) now has permission catalog, userService and Activity Log panel. ActivityLogger backend only logs employee create/update. No user CRUD backend yet. | In testing | In progress
T05 | Foundation | Company information, payroll settings, holidays | 2 | 3 | 6 | 2026-09-22 | 2026-10-05 | In progress | 40% | 100% | -60 | Behind plan | Company Settings page built (FE, mock/local stores). Backend controller and persistence pending. | In testing | Not started
T06 | Foundation | Branches and onboarding | 3 | 3 | 5 | 2026-09-29 | 2026-10-05 | In progress | 40% | 100% | -60 | Behind plan | Branches and Onboarding pages built (FE, mock), incl. add/details dialogs and branch departments panel. Branch model exists; no controller or API. | In testing | Not started
T07 | Workforce and time | Employee management (list, profile, import) | 2 | 3 | 10 | 2026-09-22 | 2026-10-05 | In progress | 65% | 100% | -35 | Behind plan | FE list, profile, add/import dialogs, bulk actions, department select and new Attendance Summary tab built. Backend: store/update endpoints, validation, activity log and EmployeeTest feature tests. List/show still read mock data. | In testing | In progress
T08 | Workforce and time | Attendance, adjustments and biometrics | 3 | 4 | 12 | 2026-09-29 | 2026-10-12 | In progress | 40% | 100% | -60 | Behind plan | Attendance page, adjustments list, daily attendance table (expanded), biometrics import and schedule review built (FE, mock). attendance.import permission added. No attendance tables or API yet. | In testing | Not started
T09 | Workforce and time | Schedules (roster, teams, shift templates) | 3 | 4 | 8 | 2026-09-29 | 2026-10-12 | In progress | 40% | 100% | -60 | Behind plan | Roster (expanded), Teams and supervisors, Shift templates, assign-shift dialog built; new ESS Schedule page (FE, mock). Backend pending. | In testing | Not started
T10 | Workforce and time | Leave types, requests, approvals and balances | 4 | 5 | 8 | 2026-10-06 | 2026-10-19 | In progress | 40% | 50% | -10 |  | Leave page built (FE, mock): leave types, requests list, grant credits, new team leave credits panel, leave duration field and preview, leave-days helper. Backend pending. | In testing | Not started
T11 | Workforce and time | Overtime and night differential | 4 | 5 | 6 | 2026-10-06 | 2026-10-19 | In progress | 40% | 50% | -10 |  | Overtime page expanded + ESS OT application built (FE, mock). Backend pending. | In testing | Not started
T12 | Workforce and time | Hourly and output compensation approvals | 5 | 6 | 6 | 2026-10-13 | 2026-10-26 | In progress | 40% | 0% | 40 |  | Approvals page built (FE, mock); compensation approval service expanded. Managers get compensation_approvals.manage. Backend pending. | In testing | Not started
T13 | Payroll and compliance | Benefits, loans and deductions | 5 | 6 | 8 | 2026-10-13 | 2026-10-26 | In progress | 40% | 0% | 40 |  | Loans and Deductions: benefits, benefit plans, loan types, employee loans, recurring/one-time deductions and transfer/add-employee dialogs built (FE, mock). Backend pending. | In testing | Not started
T14 | Payroll and compliance | Payroll computation, runs and approvals | 5 | 8 | 14 | 2026-10-13 | 2026-11-09 | In progress | 40% | 0% | 40 |  | Payroll list and period detail (both expanded), create-period dialog, computation breakdown, and new Payroll Inputs page + service built (FE, mock). Computation not yet server-side. | In testing | Not started
T15 | Payroll and compliance | Payslips (admin and employee views, email) | 7 | 8 | 6 | 2026-10-27 | 2026-11-09 | In progress | 40% | 0% | 40 |  | Payslip list/detail and payslip email service built (FE, mock). PDF/email delivery not yet server-side. | In testing | Not started
T16 | Payroll and compliance | Bonuses, incentives and 13th month pay | 7 | 8 | 8 | 2026-10-27 | 2026-11-09 | In progress | 40% | 0% | 40 |  | Bonuses and 13th month pages + payslips built (FE, mock). Backend pending. | In testing | Not started
T17 | Payroll and compliance | Statutory contributions and withholding tax | 6 | 8 | 10 | 2026-10-20 | 2026-11-09 | In progress | 40% | 0% | 40 |  | Statutory page (SSS, PhilHealth, Pag-IBIG, tax cards), withholding tax library and card (expanded), tax compliance reports built (FE, mock). Contribution tables not yet in DB. | In testing | Not started
T18 | Payroll and compliance | Reports, dashboard and notifications | 8 | 9 | 10 | 2026-11-03 | 2026-11-16 | In progress | 40% | 0% | 40 |  | Reports (basic, advanced, tax, new payroll-record and team reports, xlsx export); Admin, HR, Payroll and Manager dashboards; Notifications (expanded) built (FE, mock). Insights page is Coming Soon only. | In testing | Not started
T19 | Portals, platform and launch | Employee and Manager self-service (ESS) | 6 | 8 | 10 | 2026-10-20 | 2026-11-09 | In progress | 40% | 0% | 40 |  | ESS home, profile, payslips, attendance, overtime, leave, loans plus new Schedule and Work Output pages; My Profile route; Manager dashboard and team reports (FE, mock). Backend pending. | In testing | Not started
T20 | Portals, platform and launch | Super Admin: companies, subscription, plans | 9 | 9 | 10 | 2026-11-10 | 2026-11-16 | In progress | 25% | 0% | 25 |  | Companies page (mock) and Subscription page built. Platform user mgmt, global tax/contribution tables, support tickets, platform reports not started. | In progress | Not started
T21 | Portals, platform and launch | Integrations and API (API keys, webhooks) | 9 | 10 | 6 | 2026-11-10 | 2026-11-23 | In progress | 25% | 0% | 25 |  | Integrations page with API keys and webhooks UI built (FE, mock); connected services still Coming Soon. No backend. | In progress | Not started
T22 | Portals, platform and launch | QA testing, bug fixing and performance checks | 9 | 11 | 14 | 2026-11-10 | 2026-11-30 | Not started | 0% | 0% | 0 |  | Not started. Previous tracker had Final QA rows marked Completed; no QA evidence in the project, so reset. | Not started | Not started
T23 | Portals, platform and launch | UAT, pilot and go-live | 10 | 11 | 8 | 2026-11-17 | 2026-11-30 | Not started | 0% | 0% | 0 |  | Not started. | Not started | Not started
Total / overall |  |  |  |  | 191 |  |  |  | 39.14% | 38.74% | 0.39267 |  |  | 0.70909 | 0.13043
Notes: Progress % = average of the Frontend and Backend status (blank = not applicable); Status (I) is calculated from it. Overall progress is weighted by effort days. Frontend % and Backend % in row 32 are simple averages across tasks. 'Behind plan' = at least 25 points behind the planned % for the current week.
Formulas:
Start date = C4+([Start wk]-1)*7
End date = C4+[HOW TO USE]*7-1

## Schedule
Schedule: weekly plan with progress (target finish Nov 30, 2026)
Project Owner: Thea Consignado ¦ Light teal = scheduled weeks, dark teal = share complete, amber = current week | [15 empty] | Done portion of the task (matches Progress %)
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 | [5 empty] | Remaining / planned duration (not yet done)
ID | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Progress
| Week starts | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08
T01 | Project setup, architecture, UI/UX foundation | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
T02 | Database design and multi-tenant setup | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50%
T03 | Login, password reset, roles and permissions | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65%
T04 | User accounts, access and activity logs | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65%
T05 | Company information, payroll settings, holidays | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T06 | Branches and onboarding | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T07 | Employee management (list, profile, import) | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65%
T08 | Attendance, adjustments and biometrics | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T09 | Schedules (roster, teams, shift templates) | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T10 | Leave types, requests, approvals and balances | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T11 | Overtime and night differential | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T12 | Hourly and output compensation approvals | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T13 | Benefits, loans and deductions | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40%
T14 | Payroll computation, runs and approvals | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
T15 | Payslips (admin and employee views, email) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
T16 | Bonuses, incentives and 13th month pay | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
T17 | Statutory contributions and withholding tax | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
T18 | Reports, dashboard and notifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 40%
T19 | Employee and Manager self-service (ESS) | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
T20 | Super Admin: companies, subscription, plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25%
T21 | Integrations and API (API keys, webhooks) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 25%
T22 | QA testing, bug fixing and performance checks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0%
T23 | UAT, pilot and go-live | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0%

## Weekly
Weekly progress: planned vs actual
Project Owner: Thea Consignado ¦ Enter Actual % at the end of each week (copy Tracker J32). Leave future weeks blank.
Week | Week starts | Planned % | Actual % (enter) | Against plan (pts) | Note
0 | Start | 0% | 0% | 0
1 | 2026-09-15 | 5.41%
2 | 2026-09-22 | 13.7%
3 | 2026-09-29 | 29.84%
4 | 2026-10-06 | 38.74%
5 | 2026-10-13 | 47.91%
6 | 2026-10-20 | 56.89%
7 | 2026-10-27 | 65.88%
8 | 2026-11-03 | 77.49%
9 | 2026-11-10 | 89.35%
10 | 2026-11-17 | 95.46%
11 | 2026-11-24 | 100%
12 | 2026-12-01 | 100%
13 | 2026-12-08 | 100%

## User Stories
User Stories: Online Payroll System (OPS)
Project Owner: Thea Consignado ¦ Pick a Story status from the dropdown; Progress % is calculated from it
ID | Module | Role | User story | Acceptance criteria | Priority | Task | Task status (from Tracker) | Story status | Progress %
US01 | Accounts and access | Company Admin | As a Company Admin, I want to log in securely and log out, so that only authorized staff can open payroll data. | Login with email and password; inactive users are blocked; session ends on logout. | Must | T03 | In progress | In progress | 50%
US02 | Accounts and access | Any user | As a user, I want to reset a forgotten password by email, so that I can regain access without calling support. | Forgot password sends a reset link; reset page validates the token and password rules. | Must | T03 | In progress | In progress | 50%
US03 | Accounts and access | Company Admin | As a Company Admin, I want to assign a role to each user (HR, Payroll, Manager, Employee), so that people only see what they need. | Each role has a fixed permission list; unauthorized pages show a Forbidden page. | Must | T03 | In progress | In progress | 50%
US04 | Accounts and access | Company Admin | As a Company Admin, I want to create users and edit their roles and permissions, so that access follows our org changes. | Add, deactivate and edit users; permission changes apply on next request. | Must | T04 | In progress | In progress | 50%
US05 | Accounts and access | Company Admin | As a Company Admin, I want an activity log of key actions, so that I can audit who changed what. | Log shows user, action, target and time for employee, payroll and settings changes. | Should | T04 | In progress | In progress | 50%
US06 | Company setup | Company Admin | As a Company Admin, I want to set company information and payroll settings, so that payroll follows our policy. | Company details, pay frequency, rates and rules saved per company. | Must | T05 | In progress | In progress | 50%
US07 | Company setup | Company Admin | As a Company Admin, I want to manage holidays, so that holiday pay is computed correctly. | Add regular and special holidays; payroll reads them by date. | Should | T05 | In progress | In progress | 50%
US08 | Company setup | Company Admin | As a Company Admin, I want to manage branches and follow an onboarding checklist, so that a new company is ready for payroll. | Branch CRUD; checklist shows steps done and marks Ready for Payroll. | Should | T06 | In progress | In progress | 50%
US09 | Employees | HR Admin | As an HR Admin, I want a searchable employee list, so that I can find any employee quickly. | Search and filters by branch, status and department; data limited to own company. | Must | T07 | In progress | In progress | 50%
US10 | Employees | HR Admin | As an HR Admin, I want to add and edit an employee profile, so that records stay accurate. | Required fields validated; create and update are saved and written to the activity log. | Must | T07 | In progress | In progress | 50%
US11 | Employees | HR Admin | As an HR Admin, I want to import employees from a file, so that I do not retype the whole roster. | Import validates rows and reports errors before saving. | Should | T07 | In progress | In progress | 50%
US12 | Employees | Payroll Admin | As a Payroll Admin, I want to set each employee's pay rate and compensation type, so that payroll computes the right amount. | Monthly, daily, hourly and output-based rates supported; changes need permission. | Must | T07 | In progress | In progress | 50%
US13 | Attendance and schedules | HR Admin | As an HR Admin, I want to view and filter attendance records, so that I can check who worked and when. | Records by date, employee and status with late/absent/overtime flags. | Must | T08 | In progress | In progress | 50%
US14 | Attendance and schedules | HR Admin | As an HR Admin, I want to adjust attendance with a reason, so that errors are corrected with a trail. | Adjustment needs a reason and is logged and approvable. | Must | T08 | In progress | In progress | 50%
US15 | Attendance and schedules | HR Admin | As an HR Admin, I want to import biometric logs, so that attendance is not typed by hand. | Biometric file import maps to employees and flags unmatched rows. | Should | T08 | In progress | In progress | 50%
US16 | Attendance and schedules | HR Admin | As an HR Admin, I want a roster with shift templates, so that every employee has a schedule. | Assign shifts, rest days and flexible hours; templates reusable. | Must | T09 | In progress | In progress | 50%
US17 | Attendance and schedules | Manager | As a Manager, I want teams and supervisors set up, so that approvals go to the right person. | Teams have a supervisor; approvals route by team. | Should | T09 | In progress | In progress | 50%
US18 | Leave, overtime and approvals | HR Admin | As an HR Admin, I want to define leave types and policies, so that leave rules match company policy. | Leave types with credits, accrual and paid/unpaid setting. | Must | T10 | In progress | In progress | 50%
US19 | Leave, overtime and approvals | Employee | As an Employee, I want to file a leave request and see my balance, so that I know my remaining leave. | Request shows balance; status updates on approval or rejection. | Must | T10 | In progress | In progress | 50%
US20 | Leave, overtime and approvals | Manager | As a Manager, I want to approve or reject my team's leave and overtime, so that requests move fast. | Approver sees only subordinates; decision is logged. | Must | T10 | In progress | In progress | 50%
US21 | Leave, overtime and approvals | Employee | As an Employee, I want to file overtime and night differential requests, so that extra hours are paid. | Request has date, hours and reason; approved hours feed payroll. | Must | T11 | In progress | In progress | 50%
US22 | Leave, overtime and approvals | Payroll Admin | As a Payroll Admin, I want to review hourly and output approvals, so that only approved work is paid. | Approval queue with approve/reject and totals per employee. | Must | T12 | In progress | In progress | 50%
US23 | Leave, overtime and approvals | Payroll Admin | As a Payroll Admin, I want to see pending approvals on one screen, so that nothing blocks the payroll run. | Pending counts shown by type with links to each item. | Should | T12 | In progress | In progress | 50%
US24 | Loans, deductions and statutory | Payroll Admin | As a Payroll Admin, I want to manage benefits and allowances, so that they appear in payslips. | Benefit types and employee assignments with amounts. | Should | T13 | In progress | In progress | 50%
US25 | Loans, deductions and statutory | Payroll Admin | As a Payroll Admin, I want to record employee loans and their schedule, so that payments are deducted each period. | Loan types, amortization schedule and remaining balance. | Must | T13 | In progress | In progress | 50%
US26 | Loans, deductions and statutory | Payroll Admin | As a Payroll Admin, I want recurring and one-time deductions, so that payroll reflects all deductions. | Deductions applied by period and shown on the payslip. | Must | T13 | In progress | In progress | 50%
US27 | Loans, deductions and statutory | Payroll Admin | As a Payroll Admin, I want configurable SSS, PhilHealth and Pag-IBIG tables, so that contributions follow current rules. | Contribution tables editable and effective-dated; not hard-coded. | Must | T17 | In progress | In progress | 50%
US28 | Loans, deductions and statutory | Payroll Admin | As a Payroll Admin, I want withholding tax computed automatically, so that taxes are correct per period. | Tax computed from taxable income and shown in the breakdown. | Must | T17 | In progress | In progress | 50%
US29 | Payroll and payslips | Payroll Admin | As a Payroll Admin, I want to run payroll for a period, so that gross, deductions and net pay are computed for everyone. | Run uses attendance, approvals, loans and statutory; totals per employee. | Must | T14 | In progress | In progress | 50%
US30 | Payroll and payslips | Payroll Admin | As a Payroll Admin, I want to see the computation breakdown per employee, so that I can explain any figure. | Breakdown lists every earning and deduction line. | Must | T14 | In progress | In progress | 50%
US31 | Payroll and payslips | Company Admin | As a Company Admin, I want to approve and finalize a payroll run, so that it is locked and trusted. | Approval step; finalized runs cannot be edited. | Must | T14 | In progress | In progress | 50%
US32 | Payroll and payslips | Payroll Admin | As a Payroll Admin, I want to generate payslips, so that every employee gets a record. | Payslip generated per employee per run; printable. | Must | T15 | In progress | In progress | 50%
US33 | Payroll and payslips | Payroll Admin | As a Payroll Admin, I want to email payslips to employees, so that distribution is automatic. | Email sent per employee with delivery status. | Should | T15 | In progress | In progress | 50%
US34 | Bonuses and 13th month | Payroll Admin | As a Payroll Admin, I want to generate bonuses and incentives with payslips, so that they are paid correctly. | Bonus runs per employee with a bonus payslip. | Should | T16 | In progress | In progress | 50%
US35 | Bonuses and 13th month | Payroll Admin | As a Payroll Admin, I want to generate 13th month pay, so that it is computed from the year's earnings. | 13th month run with per-employee payslip. | Must | T16 | In progress | In progress | 50%
US36 | Reports and dashboard | Company Admin | As a Company Admin, I want a dashboard with summary cards and a payroll calendar, so that I see what needs attention. | Cards, pending requests, payroll summary, recent employees and reminders. | Should | T18 | In progress | In progress | 50%
US37 | Reports and dashboard | Payroll Admin | As a Payroll Admin, I want to export employee, payroll and statutory reports, so that I can submit and file them. | Reports export to file; filters by period and branch. | Must | T18 | In progress | In progress | 50%
US38 | Reports and dashboard | Any user | As a user, I want notifications for tasks and decisions, so that I do not miss approvals. | Bell and list with links to the item. | Could | T18 | In progress | In progress | 50%
US39 | Self-service portals | Employee | As an Employee, I want to see my profile, attendance and schedule, so that I can check my own records. | ESS shows only the logged-in employee's data. | Must | T19 | In progress | In progress | 50%
US40 | Self-service portals | Employee | As an Employee, I want to view and download my payslips, so that I do not ask HR for copies. | Payslip list and detail for own records only. | Must | T19 | In progress | In progress | 50%
US41 | Self-service portals | Manager | As a Manager, I want to see my team's attendance and pending approvals, so that I can act on them. | Manager menu shows subordinates only. | Must | T19 | In progress | In progress | 50%
US42 | Platform and integrations | Super Admin | As a Super Admin, I want to view and onboard companies, so that I can run the SaaS platform. | Company list, create and activate or suspend. | Should | T20 | In progress | In progress | 50%
US43 | Platform and integrations | Super Admin | As a Super Admin, I want to manage plans and subscriptions, so that access follows what each company pays. | Plans, company subscriptions and plan-based access. | Should | T20 | In progress | In progress | 50%
US44 | Platform and integrations | Company Admin | As a Company Admin, I want API keys and webhooks, so that our other systems can connect. | Create and revoke keys; add webhooks with events. | Could | T21 | In progress | In progress | 50%
US45 | Quality and launch | Project Owner | As the Project Owner, I want every module tested and defects fixed, so that problems are found before users see them. | Test results per module; defects fixed and retested; performance checked. | Must | T22 | Not started | Not started | 0%
US46 | Quality and launch | Project Owner | As the Project Owner, I want UAT sign-off and a pilot with a real company, so that we launch only when it works. | UAT scenarios run by real users; written sign-off before go-live. | Must | T23 | Not started | Not started | 0%
Priority: Must = needed for launch, Should = important, Could = nice to have (assumed by the author). Set each story's Status in column I (Progress % follows from it). Task status is shown for reference only.

## Story Summary
User story summary
Project Owner: Thea Consignado ¦ Counts and progress of the user stories (linked to the User Stories sheet)
Summary
Total stories | 46
Must have | 31
Should have | 13
Could have | 2
Stories done | 0
Average story progress | 47.83%
Stories by module
Module | Stories | Avg progress
Accounts and access | 5 | 50%
Company setup | 3 | 50%
Employees | 4 | 50%
Attendance and schedules | 5 | 50%
Leave, overtime and approvals | 6 | 50%
Loans, deductions and statutory | 5 | 50%
Payroll and payslips | 5 | 50%
Bonuses and 13th month | 2 | 50%
Reports and dashboard | 3 | 50%
Self-service portals | 3 | 50%
Platform and integrations | 3 | 50%
Quality and launch | 2 | 0%
All figures are formulas linked to the User Stories sheet.

## Lists
Status list: what each status counts as
Project Owner: Thea Consignado ¦ Used by the Tracker and User Stories status dropdowns
Status | Counts as progress | What it means
Not started | 0% | Work has not begun
In progress | 50% | Being built or written
In testing | 80% | Built; being tested or reviewed
Done | 100% | Finished and accepted
Change the percentages (blue) if you want a different weighting. Keep Not started at 0% and Done at 100%. Do not rename the statuses: they feed the dropdowns, counts, and charts.

## Plan calc
Plan calculation (no inputs)
Project Owner: Thea Consignado ¦ Planned fraction of each task complete by the end of each week, assuming even effort across its weeks
ID | Task | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
T01 | Project setup, architecture, UI/UX foundation | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T02 | Database design and multi-tenant setup | 0% | 33.33% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T03 | Login, password reset, roles and permissions | 0% | 33.33% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T04 | User accounts, access and activity logs | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T05 | Company information, payroll settings, holidays | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T06 | Branches and onboarding | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T07 | Employee management (list, profile, import) | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T08 | Attendance, adjustments and biometrics | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T09 | Schedules (roster, teams, shift templates) | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T10 | Leave types, requests, approvals and balances | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T11 | Overtime and night differential | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T12 | Hourly and output compensation approvals | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T13 | Benefits, loans and deductions | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T14 | Payroll computation, runs and approvals | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100%
T15 | Payslips (admin and employee views, email) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100%
T16 | Bonuses, incentives and 13th month pay | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100%
T17 | Statutory contributions and withholding tax | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100%
T18 | Reports, dashboard and notifications | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100%
T19 | Employee and Manager self-service (ESS) | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100%
T20 | Super Admin: companies, subscription, plans | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
T21 | Integrations and API (API keys, webhooks) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100%
T22 | QA testing, bug fixing and performance checks | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 66.67% | 100% | 100% | 100%
T23 | UAT, pilot and go-live | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100%